## Slide 1
NOOS annual meeting 2019 Business review

## Slide 2
Agenda
Approval minutes 2018
Review of the signatories
Election of the steering group member
Review of the decisions and actions points taken in 2019 (rapporteurs)
Priorities for 2019-2020
Decision the 3 to 5 priorities that the SG will have to implement by annual meeting 2020.
Annual meeting 2020 : date and place
AOB

## Slide 3
Approbation minutes 2018

## Slide 4
Outcome 2018 annual meeting : 24 actions points, 1/3 new
2018.01 | To organise a web-conference in order to decide the best way to get feedbacks on the fitness-for-purpose of the CMEMS products for MSFD assessments and to start an inter-comparison of the different approaches, methodologies and tools used through the NOOS members in their respective MSFD assessments. The creation of a temporary working group could also be discussed. Co-chair to invite CEFAS presenting development in CefMAT (https://emeco.azurewebsites.net/). | E. Garnacho, J. Siddorn and S. Legrand
2018.02 | To facilitate the engagement of the NOOS community in the CMEMS activities for User Uptake, Training and R&D. This should at least be done by advertising call for tenders and projects. | John Siddorn
2018.03 | To report to the CMEMS Science Advisory Committee that the numerous limitations associated to the current tender framework (administrative burden, strong IPR rules, limitation to 150.000€ on 18 month, obligation to maintain the activities well after the end of the contract, obligation to support the cost of translation of several documents from English to French by a sworn interpreter…) do prevent or strongly discourage ROOSes to submit tenders for the User Uptake, Training and R&D calls. | Glenn Nolan
2018.04 | Update survey of 2017 with focus on Expectation of the relationship between NOOS and CMEMS | Sebastien Legrand
2018.05 | To write the new NOOS strategy document | Steering group
2018.06 | To write the ToRs of the working group; A new template merging TORs and factsheets is wished less marked by EuroGOOS Create new template | Each NOOS WG and project leader
2018.07 | To circulate the exact coordinates of the new list of stations used in the BMA. This list should also include Fino1 and 3 | Marc Philippart

## Slide 5
2018.08 | To study the feasibility of an alarm service in case of extreme high and low level forecast | Marc Philippart
2018.09 | In order to attract interest of MI, to develop a demonstration case with a station at risk of flooding for which there is no tide gauge (e.g. Cork) | Marc Philippart
2018.10 | To redistribute all the BMA forecasts via a ftp site | Marc Philippart
2018.11 | UK met office should implement a ftp box to exchange sea level observations The ftp box should be circulated between forecasters. | John Siddorn Marc Philippart
2018.12 | To develop a synoptic map with sea surface anomaly (surge) . | Jacob Nielsen
2018.13 | In case of missing observations, to study the feasibility of display BMA forecast on the synoptic maps (both for sea level and sea level anomaly maps) + In any case, add explanation on the page | Jacob Nielsen with the help of Marc?
2018.14 | To clarify the conditions and feasibility to add CEFAS wavenet data in the WG. David Pearce is the person at CEFAS to be convinced to get access to the data | Caroline Gautier and Susanne Tamm.
2018.15 | To extend the BMA/Matroos to waves forecast... | Caroline Gautier, Marc Philippart and WG members
2018.16 | To send to the steering group the list of participants to each task teams | Glenn Nolan
2018.17 | NOOS-IBI ROOS collaboration -To contact IBI-ROOS co-chairs to discuss the possibility to co-locate the NOOS and IBI-ROOS annual meeting. The idea is to organise a half-day workshop on the possible synergies between the 2 ROOSes. | Co-chair

## Slide 6
2018.18 | NOOS-BOOS collaboration: To organise a skype call with interested people to discuss possible NOOS/BOOS collaborations on BMA. Person of contact in BOOS : Laura Tuomi | Martin Verlaan | First half 2019 | open
2018.19 | NOOS-BOOS collaboration on CAL-VAL.: Organise a (skype) meeting with interested people in order to identify possible NOOS-BOOS collaborations on cal.-val. activities (best practices, common python codes, etc.). Person of contact in BOOS : Thorger Brüning | Christine Pequignet | First half 2019 – meeting could be join to the NOWAPS meeting in BSH on mid October 2019 | Open
2018.20 | Short presentation (3 slides) with required information and EuroGOOS priorities, for circulation before redaction of NOOS program | Glenn Nolan | ASAP | Open
2018.20 | EuroGOOS to escalate the need for E-Hype trough agreement with EEA / Copernicus flooding alarm service (Issue : too high fee requested by SMHI) | Glenn Nolan | Annual Meeting 2019 | Open
2018.21 | Provide members with an example of Best Practices in repository | Glenn Nolan | Annual Meeting 2019 | Open
2018.22 | To exchange best practise with the NOOS community and to consider their upload to the IOC repository https://www.oceanbestpractices.net | ALL | Annual meeting 2019 | Open
2018.23 | To develop a strategy to extend NOOS activities to ecology/BGC | Steering group | Annual meeting 2019 | Open
2018.24 | Formulation of a new decision making procedure, allowing to bring the decisions closer to the technical discussion | Steering group | Annual meeting 2019 | Open

## Slide 7
Review of the signatories
New associate member : PML
24 members & associate members:
  BE : MDK, RBINS
  DE : BSH, HGZ, Univ Oldenburg
  DK : DMI, GeoMETOC (FCOO)
  FR : Ifremer, SHOM, ACRI, Meteo-France
  IR : MI
  NL : RWS, Deltares, KNMI
  NO : IMR, Met Norway, NERSC, NIVA
  SW: SMHI
  UK : Met Office, PML, NOC, CEFAS
List of POCs has been updated

## Slide 8
Attendees analysis
12 member Institutes from 6 countries (missing SW, FR, IR)
Excused members: MDK (BE), NERSC (NO), SHOM (FR), SMHI (SW), KNMI (NL), CEFAS (UK) + EuroGOOS office
Excused people: Susanne Tam, John Siddorn, Jitze van der Meulen, Patrick Gorringe, Kate Collingridge, Glenn Nolan
6 “silent” members: Ifremer, ACRI, NIVA, MI, NERC/NOC, Meteo-France

## Slide 9
New member to invite?

## Slide 10
Election
In 2018-2019, the steering group consisted of
  Henning Wehde co-chair (re-appointed in 2015);
  Sebastien Legrand co-chair (re-appointed in 2016);
  Jacob Nielsen (2016);
  Marc Philippart (2016);
  John Siddorn (re-appointed in 2017) and
  Susanne Tam (2018).
Henning’s term ends and he decided to step down from the co-chairmanship and the SG
Election of a SG member :
Election of a co-chair among the SG :
NB : In 2020, 3 elections will take place

## Slide 11
Review of the decision (Christine)

## Slide 12
Priorities for 2019-2020

## Slide 13
Annual meeting 2020
Place : IMR, Bergen, Norway
Date :
Possible thematic workshops :

## Slide 14
Any Other Business items?

## Slide 15
Short steering committee meeting
Feelings from annual meeting 2019
  What works well:
  What must be improved:
How to improve SG works : Sharing tasks and roles?